## Sheet1
Project Impact if asumption is proved invalid
Assumption # | Date Added | Phase / WorkStream | Assumption Description | Timeline | Quality | Cost | Date Invalidated
1 | 2019-11-05 | LDM | assuming customer_id as primary key in customer as it is not mentioned database |  |  | high
2 | 2019-11-05 | LDM | assuming CustomerComplaintid as primary key in CustomerComplaint as it is not mentioned database |  |  | high
3 | 2019-11-05 | LDM | assuming CustomerComplaintDetail_id as primary key in CustomerComplaintDetail as it is not mentioned database |  |  | high
4 | 2019-11-05 | LDM | assuming Locationid as primary key in Location as it is not mentioned database |  |  | high
5 | 2019-11-05 | LDM | assuming ordersid as primary key in orders as it is not mentioned database |  |  | high
6 | 2019-11-05 | LDM | assuming OrderJobServiceCorrectionid as primary key in OrderJobServiceCorrection as it is not mentioned database |  |  | high
7 | 2019-11-05 | LDM | assuming orderjobpartid as primary key in OrderJobServiceCorrectionPart as it is not mentioned database |  |  | high
8 | 2019-11-05 | LDM | assuming OrderJobid as primary key in OrderJob as it is not mentioned database |  |  | high
9 | 2019-11-05 | LDM | assuming Partid as primary key in Part as it is not mentioned database |  |  | high
10 | 2019-11-05 | LDM | assuming VehicleVINid as primary key in VehicleVIN as it is not mentioned database |  |  | high
11 | 2019-11-05 | LDM | assuming usersid as primary key in users as it is not mentioned database |  |  | high
12 | 2019-11-06 | SSA | not clear perpose of mrbwharehouse in location table |  |  | low
13 | 2019-11-06 | SSA | not clear perpose of isengineering in location table |  |  | low
14 | 2019-11-06 | SSA | not clear perpose of mrbwharehouse in location table |  |  | low
15 | 2019-11-06 | SSA | not clear perpose of odometer in location orders table |  |  | low
16 | 2019-11-06 | SSA | not clear perpose of datetime in orders orders table |  |  | low
17 | 2019-11-06 | SSA | not clear perpose of leattechnicalid in orders orders table |  |  | low
18 | 2019-11-06 | SSA | not clear perpose of iscpo in orders orders table |  |  | low
19 | 2019-11-06 | SSA | not clear perpose of VOR in orders orderjob |  |  | low
20 | 2019-11-06 | SSA | not clear perpose of Planningleadtime in orders Part |  |  | low
21 | 2019-11-06 | SSA | not clear perpose of newused in orders vehicleVIN |  |  | low
22 | 2019-11-06 | LOADING | assuming 0 is for false and 1 is for true in isvehicheoperable colmun in CustomerComplaintDetail table |  |  | low
23 | 2019-11-06 | LOADING | assuming 0 is for notenable and -1 is for enable in enable column in location table |  |  | low
24 | 2019-11-06 | LOADING | assuming 0 is for inactive and -1 is for active in isdelegateservicecenter column in location table |  |  | low
25 | 2019-11-06 | LOADING | assuming0 is for inactive and -1 is for active in ispartwarehouse colmun in location table |  |  | low
26 | 2019-11-06 | LOADING | assuming 0 is for inactive and -1 is for active in isMRBwarehouse column in location table |  |  | low
27 | 2019-11-06 | LOADING | assuming 0 is for inactive and -1 is for active in isengineering colmun in location table |  |  | low
28 | 2019-11-06 | LOADING | assuming 0 is for inactive and -1 is for active in iscustomerpickup colmun in orders table |  |  | low
29 | 2019-11-06 | LOADING | assuming 0 is for inactive and -1 is for active in israngerdrop colmun in orders table |  |  | low
30 | 2019-11-08 | LOADING | taking default value of decimal is 0.0 |  |  | low
31 | 2019-11-08 | LOADING | taking default value of bit is 0 |  |  | low